## Risk Register
CYBERSECURITY RISK REGISTER
Security Assessment • Internal Lab Environment • Prepared by Kinan
Scope: 192.168.56.101 (Metasploitable 2) only ¦ Assessor host: Kali (192.168.56.102) ¦ Method: Nmap service/version scan + Nmap NSE vulnerability scripts (--script vuln) ¦ Date: 07 October 2026
Risk ID | Asset | Vulnerability / Finding | Description | Threat / Impact | Likelihood (1-5) | Impact (1-5) | Risk Score | Risk Level | Control Reference | Treatment / Recommendation | Owner | Status | CVE / Evidence
R-001 | Metasploitable (192.168.56.101) | Backdoor root shell (port 1524/bindshell) | An open bind shell provides a direct, unauthenticated root command shell to anyone who connects. | Immediate, full root compromise of the host with no credentials required. | 5 | 5 | 25 | Critical | ISO 27001 A.8.9 / NIST PR.AC-4 | Remove the backdoor; rebuild host from a trusted image; restrict inbound access. | System Administrator | Open | Not re-tested by NSE; based on exposed bindshell service (Metasploitable root shell).
R-002 | Metasploitable (192.168.56.101) | vsftpd 2.3.4 with known backdoor (port 21) | This exact FTP version shipped with a malicious backdoor (CVE-2011-2523) opening a root shell. | Remote attacker gains root shell via a publicly documented exploit. | 5 | 5 | 25 | Critical | ISO 27001 A.8.8 / NIST ID.RA-1 | Upgrade/replace FTP service; apply patch management baseline. | System Administrator | Open | CVE-2011-2523 (vsftpd 2.3.4 backdoor). Version-based; NSE did not re-confirm.
R-003 | Metasploitable (192.168.56.101) | Telnet service exposed (port 23) | Telnet transmits all data, including credentials, in cleartext. | Network eavesdropper captures admin login and gains full access. | 5 | 4 | 20 | Critical | ISO 27001 A.8.24 / NIST PR.DS-2 | Disable Telnet; enforce SSH for remote administration. | System Administrator | Open | Confirmed open (Nmap). Cleartext protocol by design.
R-004 | Metasploitable (192.168.56.101) | r-services: rlogin/rsh/rexec (ports 512-514) | Legacy 'r' services provide remote access with weak, cleartext, trust-based authentication. | Trivial remote access and credential interception. | 4 | 4 | 16 | Critical | ISO 27001 A.8.24 / NIST PR.AC-7 | Disable rsh/rlogin/rexec; replace with SSH. | System Administrator | Open | Confirmed open (Nmap).
R-005 | Metasploitable (192.168.56.101) | FTP services in cleartext (ports 21, 2121) | File transfer protocol sends credentials and data unencrypted. | Interception of files and login credentials in transit. | 4 | 3 | 12 | High | ISO 27001 A.8.24 / NIST PR.DS-2 | Replace with SFTP/FTPS; disable anonymous access. | System Administrator | Open | Confirmed open (Nmap).
R-006 | Metasploitable (192.168.56.101) | distccd remote compiler exposed (port 3632) | Distributed compiler daemon allows remote command execution (CVE-2004-2687). | Remote code execution leading to host compromise. | 4 | 5 | 20 | Critical | ISO 27001 A.8.9 / NIST PR.IP-1 | Disable distccd unless required; restrict to trusted hosts only. | System Administrator | Open | Confirmed open (Nmap).
R-007 | Metasploitable (192.168.56.101) | UnrealIRCd backdoor (ports 6667, 6697) | The distributed UnrealIRCd package contained a backdoor (CVE-2010-2075). | Remote code execution via a known public exploit. | 4 | 5 | 20 | Critical | ISO 27001 A.8.8 / NIST ID.RA-1 | Remove/upgrade IRC daemon; verify software integrity on install. | System Administrator | Open | CVE-2010-2075 (UnrealIRCd backdoor). Version-based; NSE did not re-confirm.
R-008 | Metasploitable (192.168.56.101) | MySQL database exposed to network (port 3306) | Database engine reachable over the network, often with weak or default credentials. | Unauthorized data access, modification, or exfiltration. | 4 | 4 | 16 | Critical | ISO 27001 A.8.3 / NIST PR.AC-4 | Bind to localhost or restrict by firewall; enforce strong credentials. | Database Administrator | Open | Confirmed open (Nmap).
R-009 | Metasploitable (192.168.56.101) | PostgreSQL database exposed (port 5432) | Database engine reachable over the network with potentially weak credentials. | Unauthorized data access, modification, or exfiltration. | 4 | 4 | 16 | Critical | ISO 27001 A.8.3 / NIST PR.AC-4 | Restrict network access; enforce strong authentication. | Database Administrator | Open | Confirmed open (Nmap). CCS Injection CVE-2014-0224 (see R-018).
R-010 | Metasploitable (192.168.56.101) | SMB/Samba file sharing exposed (ports 139, 445) | Outdated Samba shares reachable on the network enable lateral movement. | Unauthorized file access and potential remote code execution. | 4 | 4 | 16 | Critical | ISO 27001 A.8.20 / NIST PR.AC-5 | Patch Samba; restrict shares; apply least-privilege access. | System Administrator | Open | Confirmed open (Nmap). MS10-054 / MS10-061: not vulnerable (NSE).
R-011 | Metasploitable (192.168.56.101) | NFS export reachable (port 2049) | Network file system export may allow mounting of shares without strong controls. | Unauthorized read/write access to shared files. | 3 | 4 | 12 | High | ISO 27001 A.8.20 / NIST PR.AC-5 | Restrict exports to trusted hosts; enforce authentication. | System Administrator | Open | Confirmed open (Nmap).
R-012 | Metasploitable (192.168.56.101) | VNC remote access, protocol 3.3 (port 5900) | Legacy VNC protocol uses weak authentication and no strong encryption. | Remote desktop takeover via weak/brute-forced authentication. | 3 | 4 | 12 | High | ISO 27001 A.8.5 / NIST PR.AC-7 | Disable or tunnel VNC over SSH; enforce strong authentication. | System Administrator | Open | Confirmed open (Nmap), protocol 3.3.
R-013 | Metasploitable (192.168.56.101) | End-of-life OS: Linux kernel 2.6.x | The host runs an unsupported, end-of-life operating system no longer receiving security patches. | Accumulating unpatched vulnerabilities across the entire system. | 5 | 5 | 25 | Critical | ISO 27001 A.8.8 / NIST ID.AM-2 | Decommission or rebuild on a supported, patched OS. | IT Management | Open | Confirmed via OS detection (Nmap): Linux 2.6.x.
R-014 | Metasploitable (192.168.56.101) | rpcbind / RPC services exposed (port 111) | RPC portmapper exposes service enumeration useful for targeting further attacks. | Reconnaissance aiding exploitation of RPC-based services. | 3 | 3 | 9 | Medium | ISO 27001 A.8.20 / NIST PR.AC-5 | Restrict RPC to trusted hosts; disable if unused. | System Administrator | Open | Confirmed open (Nmap).
R-015 | Metasploitable (192.168.56.101) | Java RMI registry RCE (port 1099) | RMI registry default configuration allows loading classes from remote URLs, enabling remote code execution. | Unauthenticated remote code execution; full host compromise. | 4 | 5 | 20 | Critical | ISO 27001 A.8.9 / NIST PR.IP-1 | Disable/secure RMI; restrict to trusted hosts; patch. | System Administrator | Open | NSE rmi-vuln-classloader: VULNERABLE.
R-016 | Metasploitable (192.168.56.101) | TLS POODLE – SSLv3 (SMTP/other) | SSLv3 with CBC padding allows a man-in-the-middle to recover cleartext (POODLE). | Interception/decryption of encrypted traffic. | 3 | 3 | 9 | Medium | ISO 27001 A.8.24 / NIST PR.DS-2 | Disable SSLv3; enforce modern TLS. | System Administrator | Open | CVE-2014-3566. NSE ssl-poodle: VULNERABLE.
R-017 | Metasploitable (192.168.56.101) | TLS Logjam / weak DH (export ciphers) | TLS supports weak/export-grade Diffie-Hellman, allowing downgrade and decryption (Logjam). | Downgrade attack enabling traffic decryption. | 3 | 3 | 9 | Medium | ISO 27001 A.8.24 / NIST PR.DS-2 | Disable export ciphers; use 2048-bit+ DH; modern TLS. | System Administrator | Open | CVE-2015-4000. NSE ssl-dh-params: VULNERABLE.
R-018 | Metasploitable (192.168.56.101) | OpenSSL CCS Injection (PostgreSQL/TLS) | OpenSSL improperly restricts ChangeCipherSpec, enabling MitM session hijacking. | Interception or tampering of TLS sessions. | 3 | 4 | 12 | High | ISO 27001 A.8.24 / NIST PR.DS-2 | Patch/upgrade OpenSSL. | System Administrator | Open | CVE-2014-0224. NSE ssl-ccs-injection: VULNERABLE (High).
R-019 | Metasploitable (192.168.56.101) | Apache Slowloris DoS (port 80) | Apache httpd is susceptible to Slowloris, exhausting connections to cause denial of service. | Web service outage from a single low-bandwidth attacker. | 3 | 3 | 9 | Medium | ISO 27001 A.8.6 / NIST PR.IP-1 | Apply mod_reqtimeout/limits; upgrade Apache. | System Administrator | Open | CVE-2007-6750. NSE http-slowloris-check: LIKELY VULNERABLE.
R-020 | Metasploitable (192.168.56.101) | Web app info exposure (phpinfo, phpMyAdmin, dir listing) | Web root exposes phpinfo.php, phpMyAdmin, directory listings and training apps revealing system info. | Information disclosure aiding targeted attacks. | 3 | 3 | 9 | Medium | ISO 27001 A.8.9 / NIST PR.AC-4 | Remove phpinfo; restrict admin tools; disable directory listing. | Web Administrator | Open | NSE http-enum: phpinfo.php, /phpMyAdmin/, /doc/, /icons/.
R-021 | Metasploitable (192.168.56.101) | HTTP TRACE method enabled (port 80) | The web server allows the HTTP TRACE method, usable in cross-site tracing attacks. | Assists credential/cookie theft via XST. | 2 | 2 | 4 | Low | ISO 27001 A.8.9 / NIST PR.AC-4 | Disable TRACE on the web server. | Web Administrator | Open | NSE http-trace: TRACE is enabled.

## Scoring Key & Summary
SCORING KEY & RISK SUMMARY
Likelihood scale |  | Findings by level
1 | Rare — very unlikely to occur | Level | Count
2 | Unlikely | Critical | 11
3 | Possible | High | 4
4 | Likely | Medium | 5
5 | Almost certain — expected to occur | Low | 1
|  | Total | 21
Impact scale
1 | Negligible — minimal effect
2 | Minor
3 | Moderate
4 | Major
5 | Severe — critical business/data loss
Risk level bands (Score = Likelihood × Impact)
Level | Score range
Low | 1 – 4
Medium | 5 – 9
High | 10 – 15
Critical | 16 – 25